{"text_format":"3","workbook":"xls","n_sheets":2,"sheets":["2016年","Sheet1"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"2016年","index":0,"n_rows":63,"n_cols":6,"rows_kept":63,"merged":[[1,0,1,5]],"flags":["formulas_cached_only"]}
[]
["2016年财税库银税收收入电子缴库横向联网上线测试时间安排"]
["任务名称","开始时间","完成时间","责任单位","备注","关键时间点"]
["第一批"]
["联调测试工作启动",null,"2016-04-29"]
["联网单位申请",null,"2016-04-29"]
[" 新上线省地税部门申请",null,"2016-04-29","有关省财政厅、地税局、人民银行"]
[" 新上线省国税部门申请",null,"2016-04-29","有关省国税局、人民银行"]
[" 新上线地方商业银行申请",null,"2016-04-29","有关省人民银行"]
[" 已上线省扩面推广申请（需联调）",null,"2016-04-29","已上线省人民银行"]
["确定联调测试地区和联网单位",null,"2016-04-29","财政部、国家税务总局、人民银行",null,"◆◆"]
["制定上报实施方案和计划",null,"2016-04-29","各联调测试省税务、人民银行"]
["软件开发及测试优化（联网单位）",null,"2016-05-23",null,null,"◆◆"]
["联网单位接口软件开发",null,"2016-05-23","联网单位"]
["联网单位相关系统改造",null,"2016-05-23","联网单位"]
["接口软件测试和优化",null,"2016-05-23","联网单位"]
["联调测试","2016-05-24","2016-06-17",null,null,"◆◆"]
["制定联调测试方案",null,"2016-05-24","各联调测试省税务、人民银行"]
["联调测试部署",null,"2016-05-24","国家税务总局、人民银行"]
["联调测试联网信息统计",null,"2016-05-24","各联调测试省税务、人民银行"]
["联网单位分配节点代码",null,"2016-05-24","人民银行"]
["测试CA证书及生产CA证书下发","2016-05-25","2016-05-26","国家税务总局、人民银行","税务生产证书、财政、地方性银行测试证书"]
["连通性测试","2016-05-27","2016-05-29","人民银行、联网单位","含网络及MQ的调整"]
["联调测试第一轮","2016-05-30","2016-06-08","人民银行、联网单位","财政可选参加，通过即可。","◆◆"]
["软件修改与完善","2016-06-10","2016-06-11","人民银行、联网单位"]
["联调测试第二轮","2016-06-12","2016-06-17","人民银行、联网单位","财政可选参加，通过即可。","◆◆"]
["软件定版",{"$nulls":4},"◆◆"]
["联网单位接口软件定版",null,"2016-07-01","联网单位"]
["生产环境集成(联网单位)","2016-07-01","2016-07-08",null,null,"◆◆"]
["软、硬件及CA证书到位",null,"2016-07-01","人民银行、联网单位","财政、地方性银行CA证书下发"]
["系统集成","2016-07-01","2016-07-02","人民银行、联网单位"]
["集成测试","2016-07-03","2016-07-04","人民银行、联网单位"]
["上线运行","2016-07-05","2016-07-08","人民银行、联网单位",null,"◆◆"]
["第二批"]
["联调测试工作启动",null,"2016-06-20"]
["联网单位申请",null,"2016-06-20"]
[" 新上线省地税部门申请",null,"2016-06-20","有关省财政厅、地税局、人民银行"]
[" 新上线省国税部门申请",null,"2016-06-20","有关省国税局、人民银行"]
[" 新上线地方商业银行申请",null,"2016-06-20","有关省人民银行"]
[" 已上线省扩面推广申请（需联调）",null,"2016-06-20","已上线省人民银行"]
["确定联调测试地区和联网单位",null,"2016-06-20","财政部、国家税务总局、人民银行",null,"◆◆"]
["制定上报实施方案和计划",null,"2016-06-20","各联调测试省税务、人民银行"]
["软件开发及测试优化（联网单位）",null,"2016-07-11",null,null,"◆◆"]
["联网单位接口软件开发",null,"2016-07-11","联网单位"]
["联网单位相关系统改造",null,"2016-07-11","联网单位"]
["接口软件测试和优化",null,"2016-07-11","联网单位"]
["联调测试","2016-07-18","2016-08-12",null,null,"◆◆"]
["制定联调测试方案",null,"2016-07-18","各联调测试省税务、人民银行"]
["联调测试部署",null,"2016-07-18","国家税务总局、人民银行"]
["联调测试联网信息统计",null,"2016-07-18","各联调测试省税务、人民银行"]
["联网单位分配节点代码",null,"2016-07-18","人民银行"]
["测试CA证书及生产CA证书下发","2016-07-21","2016-07-22","国家税务总局、人民银行","税务生产证书、财政、地方性银行测试证书"]
["连通性测试","2016-07-23","2016-07-24","人民银行、联网单位","含网络及MQ的调整"]
["联调测试第一轮","2016-07-25","2016-08-05","人民银行、联网单位","财政可选参加，通过即可。","◆◆"]
["软件修改与完善","2016-08-06","2016-08-07","人民银行、联网单位"]
["联调测试第二轮","2016-08-08","2016-08-12","人民银行、联网单位","财政可选参加，通过即可。","◆◆"]
["软件定版",{"$nulls":4},"◆◆"]
["联网单位接口软件定版",null,"2016-08-31","联网单位"]
["生产环境集成(联网单位)","2016-09-01","2016-09-09",null,null,"◆◆"]
["软、硬件及CA证书到位",null,"2016-09-01","人民银行、联网单位","财政、地方性银行CA证书下发"]
["系统集成","2016-09-01","2016-09-02","人民银行、联网单位"]
["集成测试","2016-09-03","2016-09-04","人民银行、联网单位"]
["上线运行","2016-09-05","2016-09-09","人民银行、联网单位",null,"◆◆"]

{"sheet":"Sheet1","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}